## Cover
Scrum Reporting Form
| Day | 2024-10-31
| Due Date | 2024-11-04
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
| GitHub Repository: | https://github.com/JonathanBurg/Mancala-MASM
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| boardController | Jonathan Burgener
You have had an opportunity to decide on a project and start the general set-up for the project. The next step is to go through and identify all the tasks that need to be commpleted to have a finished product for the Final Project Presentation. The Fibonacci Sequence to assign importance of each task. Rate the tasks by the importance of when they need to be done as well as the importance to the completion of the project. Some tasks with a low priority may never be completed. Those can be saved for a later project. Come back to this list each day, mark tasks that have been completed as "Done" and repriotize the remaining tasks.
| Plans for | 2024-11-04
| Team Member | Tasks planned | Priority
| All | Decide on Project | 1
| All | Identify major parts of the project | 2
| All | Set up GitHub account and invite all participants including WayneWCook | 3
Scrum Reports are based on Stories. Create a good story about what you want your project to do when it is completed.Tasks are often assigned as stories, with the author telling what they want each new portion of the project to do when it is complete.
| Story behind your project | A good game of Mancala can be hard to find. So I've been working to create a version of Mancala with as many programming languages as I can (with this being language number 3, after Java and C++). The game will have 2 DW arrays to store the number of stones in the 6 pits for each side and two DW variables for the number of stones in the Mancalas on the ends of the board. There will be 5 modules: one controlling the stones, one for printing the board, one for managing user input, the main module, and a read-write module. The module for managing user input will act as the driver for the program. The game will be turn based, with the board flipping after each move so the pits for the active player are on the bottom and their Mancala on the right. During a turn the active player will input a number to pick a pit on their side. The selected pit will be cleared and for the number of stones in the selected pit, each successive pit will be incremented, excluding the other player's Mancala. If the final stone lands in the active player's Mancala, they will get another turn. If the final stone ends in an empty pit on the active players side, that last stone and all the stones in the pit on the opposite side will be moved to the active player's Mancala. The game will end when there are no more uncaptured stones on the active player's side, or when there are no more uncaptured stones. The winner will be the player with the most stones in their Mancala. For the interface, an external library may be used to provide coloring to prevent mix-ups between who's turn it is.

## 4 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-11-04 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-11-07
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| boardController | Jonathan Burgener
| Tasks Due | 2024-11-04 | Priority
| Team Member | Tasks planned
| All | Decide on Project | 1 | DONE
| All | Identify major parts of the project | 2 | DONE
| All | Set up GitHub account and invite all participants including WayneWCook | 3 | DONE
| Plans for | 2024-11-07
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | 1
| Jonathan Burgener | Create Stubs and write main method. | 2
| Jonathan Burgener | Get basic controls set up | 3

## 7 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-11-07 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-11-11
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| boardController | Jonathan Burgener |  | Removed to combine boardController and board
| Tasks Due | 2024-11-07 | Priority
| Team Member | Tasks planned
| All | Break up project into modules (use UML diagrams) | 1 | Have a hard time figuring out what is needed before I complete each part of the program
| Jonathan Burgener | Create Stubs and write main method. | 2 | DONE
| Jonathan Burgener | Get basic controls set up | 3 | DONE
| Plans for | 2024-11-11
| Team Member | Tasks planned
| Jonathan Burgener | Create basic board | 2
| Jonathan Burgener | Research formatting the console output in MASM | 3
| Jonathan Burgener | Break up project into modules (use UML diagrams) | 1

## 11 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-11-11 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-11-14
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| Tasks Due | 2024-11-11 | Priority
| Team Member | Tasks planned
| Jonathan Burgener | Create basic board | 2 | Done. Ran into issues with Unicode, but got it figured out.
| Jonathan Burgener | Research formatting the console output in MASM | 3
| Jonathan Burgener | Break up project into modules (use UML diagrams) | 1 | Just going to push to the end when I have everything figured out.
| Plans for | 2024-11-14
| Team Member | Tasks planned
| Jonathan Burgener | Connect controls to board | 1
| Jonathan Burgener | Create win state | 2

## 14 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-11-14 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-11-25
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| Tasks Due | 2024-11-14 | Priority
| Team Member | Tasks planned
| Jonathan Burgener | Connect controls to board | 1
| Jonathan Burgener | Create win state | 2
| Plans for | 2024-11-25
| Team Member | Tasks planned
| Jonathan Burgener | Set up edge case scenarios (capturing, extra move, etc.) | 1

## 25 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-11-25 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-11-28
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| Tasks Due | 2024-11-25 | Priority
| Team Member | Tasks planned
| Jonathan Burgener | Set up edge case scenarios (capturing, extra move, etc.) | 1
| Plans for | 2024-11-28
| Team Member | Tasks planned for Project Presentration
| Jonathan Burgener | Pretty up the board | 2
| Jonathan Burgener | Break up project into modules (use UML diagrams) | 1

## 28 Nov
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-11-28 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-12-02
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| Tasks Due | 2024-11-28 | Priority
| Team Member | Tasks planned
| Jonathan Burgener | Pretty up the board | 2
| Jonathan Burgener | Break up project into modules (use UML diagrams) | 1
| Plans for | 2024-12-02
| Team Member | Tasks planned for Project Presentration

## 2 Dec
Scrum Reporting Form |  |  | Priority | Status
| Date | 2024-12-02 |  | Either DONE or what problem needs to be solved before the task can be completed.
| Due Day | 2024-12-05
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| Tasks Due | 2024-12-02 | Priority
| Team Member | Tasks planned
| Plans for | 2024-12-05
| Team Member | Tasks planned for Project Presentration
| Jonathan Burgener | Video Presentation to describe project & slides | 1
| Jonathan Burgener | Final Scrum Report (this document) | 2
| Jonathan Burgener | Slide Presentation | 3
| Jonathan Burgener | Project Submittal | 4

## Final
Scrum Reporting Form |  |  | Priority | Status | Final Thoughts on this Process
| Day | 2024-12-05 |  | Either DONE or what problem needs to be solved before the task can be completed. | This page is the last Scrum Form due and is to record your final thoughts on the process
| Due Day | 2024-12-06
| Team Name: | Manaca
| Team Members: | Jonathan Burgener
| Project: | ASCII Mancala Game
Division of Labor
| Module Name | Author
| main | Jonathan Burgener
| readWrite | Jonathan Burgener
| controller | Jonathan Burgener
| board | Jonathan Burgener
| Tasks Due | 2024-12-05
| Team Member | Presentaion | Priority
| Jonathan Burgener | Video Presentation to describe project & slides | 1
| Jonathan Burgener | Final Scrum Report (this document) | 2
| Jonathan Burgener | Slide Presentation | 3
| Jonathan Burgener | Project Submittal | 4
| Plans for | 2024-12-06
| Team Member | Tasks planned
| ALL | None - complete